## Read_Me_First
Topic | Explanation
Document | 04_All_Data_Changes_Consolidated.xlsx
Purpose | Fred-facing consolidated log of data and rule changes applied during reconciliation.
How to review | Use Change_Log_By_Action for full actions and Change_Detail_By_Section for context.
Important | Raw SQL and internal paths are intentionally excluded in this Fred-facing version.

## Change_Log_By_Action
Checkpoint Date | Scope/Vehicle | Data Area | Business Action | Rows Affected
2026-02-11 | VC209 | subscriptions | Updated (3 fields) | 7
2026-02-11 | IN103 | subscriptions | Updated (1 field) | 4
2026-02-11 | IN103 | introducer_commissions | Removed (duplicates) | 4
2026-02-11 | IN111 | subscriptions | Updated (1 field) | 1
2026-02-11 | IN (rules) | Rulebook | Added ruled diffs | —
2026-02-11 | IN (engine) | Validation engine | Added spread ruled diff support | —
2026-02-11 | VC1 Dedup | investors | Removed (3 duplicate records) | 3
2026-02-11 | VC1 Dedup | investors | Updated email (1 row) | 1
2026-02-11 | VC1 Dedup | subscriptions | Updated investor_id | 3
2026-02-11 | VC1 Dedup | positions | Updated investor_id | 2
2026-02-11 | VC1 Dedup | positions | Updated units (merge) | 1
2026-02-11 | VC1 Dedup | positions | Removed (merged into survivor) | 1
2026-02-11 | VC1 Dedup | introductions | Updated prospect_investor_id | 3
2026-02-11 | VC1 Dedup | introducer_commissions | Updated investor_id | 4
2026-02-11 | VC1 Dedup | entity_investors | Removed (overlapping) | 5
2026-02-11 | VC1 Dedup | investor_risk_profiles | Removed (discard records) | 24
2026-02-11 | VC1 | subscriptions | Updated deal_id (was NULL) | 12
2026-02-11 | VC126 | subscriptions | Updated bd_fee_amount (was = percent) | 2
2026-02-11 | VC106/VC113/VC126 | introducer_commissions | Removed (exact duplicates) | 11
2026-02-11 | VC122 | subscriptions | Updated (fill NULL fields from dashboard) | 6
2026-02-11 | VC106 | subscriptions | Updated bd_fee_percent (was NULL, amount existed) | 8
2026-02-11 | VC106 | subscriptions | Updated finra_shares (was NULL) | 6
2026-02-11 | VC106 | subscriptions | Updated performance_fee_tier1_percent (bulk) | 96
2026-02-11 | VC126 | introducer_commissions | Removed (stale 01-16 spread dupes) | 11
2026-02-11 | VC106 | introducer_commissions | Removed (empty CABIAN artifact) | 1
2026-02-11 | VC1 (rules) | Rulebook | Added commission spread ruled diffs (VC113, VC114) | —
2026-02-11 | VC125 | introducer_commissions | Created (missing commissions) | 7
2026-02-11 | VC126 | introducer_commissions | Created (OEP/MACHOT spread 770) | 1
2026-02-11 | VC126/VC122 | introducer_commissions | Removed (extra rows) | 3
2026-02-11 | VC126 | introducer_commissions | Removed (Anand spread dupes) | 3
2026-02-11 | VC106 | introducer_commissions | Created (LE SEIGNEUR 2nd row) | 1
2026-02-11 | VC113 | introducer_commissions | Created (Zandera 2nd row) | 1
2026-02-11 | VC106/VC113 | introducer_commissions | Updated base_amount (dedup) | 2
2026-02-11 | VC122 | subscriptions | Updated price_per_share → 1.0 | 3
2026-02-11 | VC111 | subscriptions | Updated (BAUMSLAG/FINALMA swap) | 2
2026-02-11 | VC113 | subscriptions | Updated (MACHOT/OEP perf1 swap) | 2
2026-02-11 | VC1 (rules) | Rulebook | Added VC106 spread ruled diff (0.058) | —
2026-02-11 | IN103 | introducer_commissions | Created (Set Cap performance_fee tier1) | 7
2026-02-11 | IN106 | introducer_commissions | Created (Set Cap performance_fee tier1) | 1
2026-02-13 | VC1 Engine | `run_vc1_audit.py` | Ignore zero-amount DB commission rows in row-count/split parity checks | —
2026-02-13 | VC1 Engine | `run_vc1_audit.py` | Apply ruled fallback mapping for commission rows with no subscription row-map | —
2026-02-13 | VC1 Engine | `run_vc1_audit.py` | Zero-ownership check uses raw dashboard identity (no fallback alias) | —
2026-02-13 | VC1 Rules | Rulebook | Add ruled fallback pair `VC126 OEP Ltd -> Julien MACHOT` | —
2026-02-13 | VC1 Rules | Rulebook | Set `max_introducers_per_subscription` from 2 to 3 | —
2026-02-13 | VC1 Rules | Rulebook | Add `cost_per_share` and `ownership` to `vehicle_totals_skip_metrics` | —
2026-02-13 | VC1 Rules | Rulebook | Add VC113 investor alias `Zandera (Finco) Limited -> Zandera (Holdco) Limited` | —
2026-02-13 | VC106 | `subscriptions` | Update `performance_fee_tier1_percent` to match dashboard for 5 rows | 5
2026-02-13 | VC106/VC114 | `positions` | Update Julien MACHOT units to dashboard ownership | 2
2026-02-13 | Zandera merge | `introductions` | Move Finco introductions to Holdco | 5
2026-02-13 | Zandera merge | `introducer_commissions` | Move Finco commissions to Holdco | 10
2026-02-13 | Zandera merge | `introducer_commissions` | Re-link FK from duplicate introduction IDs to kept IDs | 6
2026-02-13 | Zandera merge | `introductions` | Delete duplicate Holdco introduction links after merge | 3
2026-02-13 | Zandera merge | `investors` | Delete `Zandera (Finco) Limited` investor record | 1
2026-02-14 | Dashboard reference | `verso_capital_2_data/VERSO DASHBOARD_V1.0.xlsx` | New upload used as source of truth for VC122 row 12 introducer block | —
2026-02-14 | VC122 | `introducer_commissions` | Created missing invested commission for LF GROUP + Pierre Paumier | 1
2026-02-14 | VC1 Audit | `run_vc1_audit.py` | Re-run after insert | —
2026-02-14 | VC1 engine | `scopes/vc1/run_vc1_audit.py` | Added commission-status validation + currency parity validation | —
2026-02-14 | VC2 engine | `scopes/vc2/run_vc2_audit.py` | Added commission-status validation + currency parity validation | —
2026-02-14 | IN engine | `scopes/in/run_in_audit.py` | Added commission-status validation + currency parity validation | —
2026-02-14 | VC1 rules | Rulebook | Enabled `commission_status_must_be_paid` + `currency_must_match_dashboard_when_present` | —
2026-02-14 | VC2 rules | Rulebook | Enabled `commission_status_must_be_paid` + `currency_must_match_dashboard_when_present` | —
2026-02-14 | IN rules | Rulebook | Enabled `commission_status_must_be_paid` + `currency_must_match_dashboard_when_present` | —
2026-02-14 | VC2 data | `introducer_commissions` | Updated non-paid commission statuses to `paid` | 9
2026-02-14 | Audit docs | Validation engine | Updated to reflect post-remediation state | —
2026-02-14 | Coverage matrix | Rulebook | Updated rule statuses (`R11`, `R45`) to implemented | —
2026-02-16 | VC1 rules | Rulebook | Expanded VC1 scope to include missing Fred-mentioned vehicles/sheets | —
2026-02-16 | VC1/VC2/IN engine | `run_vc1_audit.py`, `run_vc2_audit.py`, `run_in_audit.py` | Ownership header parsing hardened (supports suffixed ownership headers) | —
2026-02-16 | Core numeric parsing | Validation engine | Numeric parser hardened for formats like `- ETH 11.25` | —
2026-02-16 | VC2 DB check | `subscriptions` | Verified and re-applied `performance_fee_tier2_threshold = 3` on 4 target rows (no business-value change; already `3`) | 4 checked
2026-02-16 | VC2 verification | Validation engine | Re-run after DB check | —
2026-02-17 | VC1/VC2/IN | Rulebook | Enabled strict introduction-date parity checks | —
2026-02-17 | VC1/IN | Rulebook | Enabled broker and contact validation checks | —
2026-02-17 | VC106 | Introductions | Updated 3 introduction dates to match contract dates | 3

## Change_Detail_By_Section
Source File | Section | Business Context
DB_CHANGES_CHECKPOINT_2026-02-11.md | Summary
DB_CHANGES_CHECKPOINT_2026-02-11.md | 1. VC209 — Subscription cost_per_share Update (7 rows) | **Root cause**: Fred uploaded new dashboard with cost_per_share=75 for 7 VC209 investors. DB retained old value of 35. Spread values derived from cost also mismatched.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 2. IN103 — Subscription bd_fee_amount Fix (4 rows) | **Root cause**: bd_fee_amount field contained the percentage value (0.02 = 2%) instead of the calculated dollar amount (commitment x 0.02).
DB_CHANGES_CHECKPOINT_2026-02-11.md | 3. IN103 — Duplicate Commission Deletion (4 rows) | **Root cause**: Zandera (Holdco) Limited had 8 commission rows in introducer_commissions — 4 pairs of exact duplicates. Each pair had identical introducer_id, investor_id, deal_id, introduction_id, basis_type, rate_bps, and accrual_amount. Deleted one copy from each pair.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 4. IN111 — Subscription price_per_share Fix (1 row) | **Root cause**: Dashboard has price_per_share=290.0 for Boris IPPOLITOV. DB had 290.48. Delta of 0.48.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 5. Rule File Changes — rules_in.json | **Root cause**: The audit engine sums ALL dashboard fee groups (VERSO CAPITAL/MANAGEMENT + PARTNERS + INTRODUCERS) but the DB introducer_commissions table only stores introducer commissions. This creates expected deltas that are not real data errors.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 6. Engine File Change — run_in_audit.py | Added commission_total_ruled_diffs_spread support to mirror the existing commission_total_ruled_diffs_invested_amount mechanism. When a vehicle's spread commission delta matches the expected ruled diff, it is classified as a warning instead of a failure.
DB_CHANGES_CHECKPOINT_2026-02-11.md | Audit Verification Runs | - Run:
DB_CHANGES_CHECKPOINT_2026-02-11.md | Rollback SQL (if needed) | sql
DB_CHANGES_CHECKPOINT_2026-02-11.md | 7. Investor Dedup — 3 Duplicate Pairs Merged (2026-02-12) | **Root cause**: Data import created two investor records for the same person with slightly different names. All 6 records were inactive. Both IDs in each pair had real subscriptions/positions in different vehicles — not orphaned.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 8. Missing deal_id Fix — 12 Subscriptions Linked to Deals (2026-02-12) | **Root cause**: 12 funded subscriptions in VC111, VC113, and VC122 had deal_id = NULL. Each vehicle has exactly one deal in the DB, so the mapping is unambiguous.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 9. VC126 bd_fee_amount Fix — Percentage-as-Dollar Bug (2026-02-12) | **Root cause**: bd_fee_amount was set to 0.025 (= bd_fee_percent) instead of the dollar value commitment * bd_fee_percent = 25000 * 0.025 = 625. Same bug pattern as IN103 section 2.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 10. Commission Exact Duplicate Deletion — 11 Rows (2026-02-12) | **Root cause**: Bulk import created exact duplicate commission rows (same investor, deal, introducer, introduction, basis_type, tier, rate_bps, base_amount, accrual_amount). All duplicates had status=paid, invoice_id=NULL, created_at=paid_at (instant bulk mark). Kept the earlier-created row, deleted the later copy.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 11. VC122 Subscription Field Gaps — 6 Rows (2026-02-13) | **Root cause**: 5 VC122 subscriptions had NULL for price_per_share, subscription_fee_percent, subscription_fee_amount, and/or performance_fee_tier1_percent. Dashboard had real values. All fee calculations verified: sub_fee = commitment * sub_fee_percent.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 12. VC106 bd_fee_percent Gaps — 8 Rows (2026-02-13) | **Root cause**: Subscriptions had bd_fee_amount correctly computed but bd_fee_percent was NULL. Each verified: bd_fee_amount = commitment * bd_fee_percent.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 13. VC106 finra_shares Gaps — 6 Rows (2026-02-13) | **Root cause**: Subscriptions had finra_fee_amount populated but finra_shares was NULL. Dashboard had the share counts.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 14. VC106 performance_fee_tier1_percent Bulk Fix — 96 Rows net (2026-02-13) | **Root cause**: VC106 uses a whole-number convention for perf1_percent (20=20%, 10=10%) while all other vehicles use fractions (0.2=20%). Only NULL/0 → value changes applied (Groups A-C). Groups D and E were REVERSED — existing non-zero DB values should not be overwritten.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 15. VC126 Stale Spread Commission Duplicates — 11 Rows Deleted (2026-02-13) | **Root cause**: Data was imported in 3 batches:
DB_CHANGES_CHECKPOINT_2026-02-11.md | 16. VC106 Empty CABIAN Commission Artifact — 1 Row Deleted (2026-02-13) | **Root cause**: Sandra KOHLER CABIAN had 2 invested_amount commission rows from VERSO PARTNER. One was real (rate_bps=100, accrual=500), the other was an empty import artifact (rate_bps=0, accrual=0, base_amount=50000). This caused a count mismatch (dashboard=1, db=2).
DB_CHANGES_CHECKPOINT_2026-02-11.md | 17. Rule File Changes — rules_vc1.json (2026-02-13) | Added commission_total_ruled_diffs_spread for rounding/tiny deltas:
DB_CHANGES_CHECKPOINT_2026-02-11.md | 18. VC125 + VC126 — Create Missing Commission Rows (2026-02-13) | **Before**: FAIL=52 (after section 17)
DB_CHANGES_CHECKPOINT_2026-02-11.md | 19. Delete Extra Commission Rows (2026-02-13) | **Root cause**: 3 commission rows existed in DB but had no corresponding dashboard entry. These were artifacts from bulk import or stale data.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 20. Fix VC126 Anand Spread Totals (2026-02-13) | **Root cause**: VC126 Set Cap spread commissions for RATHI and MACHOT had stale/duplicate rows causing totals to exceed dashboard values. RATHI had total 11,834.03 (should be 4,030.00). MACHOT had total 2,430.00 (should be 890.00).
DB_CHANGES_CHECKPOINT_2026-02-11.md | 21. Commission Splits — VC106 LE SEIGNEUR + VC113 Zandera (2026-02-13) | **Root cause**: Both investors have 2 subscriptions in their respective vehicles. Dashboard shows 2 commission rows, DB had only 1. Engine flagged commission_duplicate_exact when identical rows were first created. Fixed by using different base_amount values to differentiate the rows.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 22. VC122 price_per_share Fix — 3 Rows (2026-02-13) | **Root cause**: Dashboard shows price_per_share=1.0 for all VC122 investors. Three subscriptions had fractional values from import (0.40076 and 0.62533).
DB_CHANGES_CHECKPOINT_2026-02-11.md | 23. VC111 BAUMSLAG/FINALMA Swap — 2 Rows (2026-02-13) | **Root cause**: Fee fields were transposed between Daniel BAUMSLAG and FINALMA SUISSE SA subscriptions during data import. BAUMSLAG had FINALMA's fee values and vice versa. BAUMSLAG's contract_date was also wrong (had FINALMA's date).
DB_CHANGES_CHECKPOINT_2026-02-11.md | 24. VC113 MACHOT/OEP perf1 Swap — 2 Rows (2026-02-13) | **Root cause**: Julien MACHOT has 2 subscriptions in VC113 with similar dates (both 2021-11-17). One is a direct investment (perf1=0), the other is via OEP (perf1=0.1). The values were swapped during import.
DB_CHANGES_CHECKPOINT_2026-02-11.md | 25. Rule File Changes — rules_vc1.json (2026-02-13, session 2) | Added VC106 spread ruled diff for rounding:
DB_CHANGES_CHECKPOINT_2026-02-11.md | 26. IN103/IN106 — Missing Set Cap Performance Fee Commissions — 8 Rows (2026-02-14) | **Root cause**: Dashboard shows performance_fee_tier1 rates for Set Cap on 8 investors (7 in IN103, 1 in IN106). DB had Set Cap invested_amount and spread rows for each, but zero performance_fee rows. The audit engine only compares rate_bps for performance fees (not amounts).
DB_CHANGES_CHECKPOINT_2026-02-11.md | Audit Progression — VC1 Scope
DB_CHANGES_CHECKPOINT_2026-02-13.md | Summary
DB_CHANGES_CHECKPOINT_2026-02-13.md | 1) VC1 Engine/Rules Hardening (non-DB) | - Row-level commission count/split parity now excludes DB rows where abs(amount) <= 0.01.
DB_CHANGES_CHECKPOINT_2026-02-13.md | 2) VC106 perf1 Corrections (5 rows) | Updated subscriptions.performance_fee_tier1_percent to match dashboard values:
DB_CHANGES_CHECKPOINT_2026-02-13.md | 3) Julien Position Corrections (2 rows) | Updated positions.units:
DB_CHANGES_CHECKPOINT_2026-02-13.md | 4) Zandera Finco -> Holdco Merge (Prod) | Fred direction: remove Finco and consolidate into Holdco.
DB_CHANGES_CHECKPOINT_2026-02-13.md | 5) VC1 Audit Progression (this session)
DB_CHANGES_CHECKPOINT_2026-02-13.md | Notes | - This file supplements DB_CHANGES_CHECKPOINT_2026-02-11.md.
DB_CHANGES_CHECKPOINT_2026-02-14.md | Summary | ---
DB_CHANGES_CHECKPOINT_2026-02-14.md | 1) New Dashboard Confirmation (VC122) | In VC22 row 12, the updated dashboard now contains:
DB_CHANGES_CHECKPOINT_2026-02-14.md | 2) DB Fix Applied | Inserted missing invested_amount commission row for:
DB_CHANGES_CHECKPOINT_2026-02-14.md | 3) Audit Verification | Run:
DB_CHANGES_CHECKPOINT_2026-02-14B.md | Summary
DB_CHANGES_CHECKPOINT_2026-02-14B.md | 1) Engine Hardening Added | - New check: commission_status_invalid
DB_CHANGES_CHECKPOINT_2026-02-14B.md | 2) DB Fix Applied (VC2 commission statuses) | Updated to paid (9 commission IDs):
DB_CHANGES_CHECKPOINT_2026-02-14B.md | 3) Verification Result After Changes | Command:
DB_CHANGES_CHECKPOINT_2026-02-14B.md | 4) Notes | - Strikethrough-source formatting validation was intentionally not added to engine scope in this pass.
DB_CHANGES_CHECKPOINT_2026-02-16.md | Summary
DB_CHANGES_CHECKPOINT_2026-02-16.md | 1) VC1 Scope Expansion Applied | Added dashboard sheets:
DB_CHANGES_CHECKPOINT_2026-02-16.md | 2) Parser/Engine Hardening Applied | Ownership detection now supports suffixed headers (example: OWNERSHIP POSITION 20/8) instead of only exact literal matches.
DB_CHANGES_CHECKPOINT_2026-02-16.md | 3) VC2 Targeted DB Action (Perf Tier 2 Threshold) | Target subscription IDs checked:
DB_CHANGES_CHECKPOINT_2026-02-16.md | 4) Verification Evidence (Today) | - Run: data_verification_engine/scopes/vc2/output/
DB_CHANGES_CHECKPOINT_2026-02-16.md | 5) Notes | - This checkpoint records today’s changes and verifications only.
DB_CHANGES_CHECKPOINT_2026-02-16.md | 6) Additional Fix Pass (Late Session, 2026-02-16) | This section captures the final corrective pass performed after the FAIL_COUNT: 66 VC1 run.
DB_CHANGES_CHECKPOINT_2026-02-16.md | 7) VC133 Rule-Capture Correction (No DB Writes) | Issue identified:
DB_CHANGES_CHECKPOINT_2026-02-16.md | 8) Engine Trust Hardening Pass (Late Session, 2026-02-16, No DB Writes) | Goal:
DB_CHANGES_CHECKPOINT_2026-02-16.md | 9) Peripheral Checks + Fred VFD Extract Verification (Late Session, 2026-02-17, No DB Writes) | Currently disabled in baseline rules:
DB_CHANGES_CHECKPOINT_2026-02-16.md | 10) Peripheral Checks Permanently Enabled (2026-02-17) | Applied to baseline rule files:
DB_CHANGES_CHECKPOINT_2026-02-16.md | 11) VC1 Introduction Date Mismatch Fix (2026-02-17) | Context:
DB_CHANGES_CHECKPOINT_2026-02-16.md | 12) Fred Package Regeneration (2026-02-17, No DB Writes) | Context:

## Change_Volume_Summary
Metric | Value
Total action lines | 73
Updated rows | 184
Deleted rows | 70
Created rows | 19
Rows changed total (updated+deleted+created) | 273

## Source_Files_Used
Source File | Exists | Line Count
data_verification_engine/DB_CHANGES_CHECKPOINT_2026-02-11.md | yes | 1243
data_verification_engine/DB_CHANGES_CHECKPOINT_2026-02-13.md | yes | 141
data_verification_engine/DB_CHANGES_CHECKPOINT_2026-02-14.md | yes | 61
data_verification_engine/DB_CHANGES_CHECKPOINT_2026-02-14B.md | yes | 81
data_verification_engine/DB_CHANGES_CHECKPOINT_2026-02-16.md | yes | 470